## Cases
Sr No | Application | Issue | Status | Developer Name | Reported Date | Fixed Date | Image Reference (Sheet 2) | Git Issue Id | Git Issue Link
1 | Eportal | For ticket requests with status "In Process" or "Approved", only the Delete option should be displayed. | New | Sunil | 15/07/26 |  | 2 | 10 | https://github.com/SDLHODDR/SDLHUB/issues/10
3 |  | The update functionality for ticket requests is not working as expected. Additionally, the Save and Authorization actions are non-functional and need to be fixed. | New |  |  |  | 2
4 |  | The ticket request list should display only those records that were raised by the currently logged-in user | New
5 |  | When the user begins typing in the search field, the screen becomes blank. This indicates a rendering or data-handling bug that must be resolved for Leave,Outdoor and Ticket booking Form | New |  |  |  | 4
6 |  | Even when the Delete option is visible (as per condition #1), clicking on the Delete button does not perform the intended action. The ticket request list should display only those records that were raised by the currently logged-in user. | New |  |  |  | 1
7 |  | In leave model the leaves CL,OL,PL and SL data is not correct for logged in user | New |  |  |  | 3
8 |  | Leave code does not contains PL option even when days are present in this type. | New
9 |  | “CL cannot be taken more than 3 times or more than 2 days” this is message has been displayed to every user whoever is selecting CL as leave code. | New |  |  |  | 3
10 |  | While saving Leave validations are not working. Even when user don’t have any balance left user can still able to apply for leave. | New
|  | Ticket booking request model, “Suitable Arrival Onwards” can be greater if train is coming next day from the date of traveling | New |  |  |  | 5
11 |  | Duplicate “Admin” profiles in Profile Access form | New | Savita | 16/07/2026 |  | 6
12 |  | In the Profile users section, the listing should show only currently active employees. | New |  |  |  | 7
13 |  | Remove Reset button or Reload the form section without loading the header section | New |  |  |  | 7
14 |  | The display format for the Policy section within the Policy/Documents menu must be consistent with the format currently applied to "My Documents." | New
15 |  | Remove either the Policy section under Policy/Documents or the Company Policy section under Maintenance. | New
16 |  | When a user accepts a Policy document, the acceptance timestamp (date and time) should be captured and shown within the Policy section. | New
17 |  | In the Employee Access form, add a filter field for Employee that allows users to search and retrieve data for a specific employee. | New |  |  |  | 8
18 |  | The Employee Access form must allow row-level editing only when the associated checkbox is checked. All rows should remain disabled until a checkbox is selected. | New |  |  |  | 8
19 |  | The Date and Requested Date fields in the Conference Room form must display dates in the "dd-Mon-YYYY" format. This format should be standardized across all modules of the application. | New |  |  |  | 9
20 |  | In the Add Conference Booking modal, the "Booking By" field is showing duplicate employee code entries (displayed twice). |  |  |  |  | 10
21 |  | In the Add Conference Booking modal, do not impose any limit on the number of attendees allowed per booking. |  |  |  |  | 10
22 |  | In the Add Conference Booking modal, ensure the Date field has the same height as all other input fields for visual consistency. |  |  |  |  | 10
23 |  | Ensure that a consistent calendar format is used and standardized across all modules of the application. | New | Sunil |  |  | 10
24 |  | Remove the Full Screen icon/frame from the top-right corner of the header area. | New | Sunil/Savita |  |  | 2
25 |  | Ensure that all buttons have a consistent UI design across every module of the application. | New | Sunil/Savita |  |  | 10

## Reference
1 | 2 | 3 | 4 |  | 5
6 | 7 | 8 |  | 9 |  | 10